## Ark1
# Blev Færdig med i de første 2 dage (dvs. 31/05 og 01/06) af projektet:
* Models
* E/R Diagram
* Mockups
* LogIn Repository/Interface
* Database/TecH3ProjectDbContext
# Domains/Models
* BaseModel /Complete
* Login /Complete
* Order /Complete
* OrderItem /Complete
* Picture /Complete
* Product /Complete
* Product_Property /Complete
* Property /Complete
* Type /Complete
* User /Complete
# Repositories og Interfaces
* LogIn: complete*2
* Order: Complete*2
* OrderItem: Double check.
* Picture: Complete*2
* Product: double check
* Product_Property: Double check
* Property: Complete?
* Type: complete
* User: Complete
# Tests for Repositories: 45 min average. |  |  | Etime | ActTime
* LogIn / |  |  | 45 |  | 10:20 - 10:35 -12:00 - 12.55/9:30 - 11:30
* Order |  |  | 45 |  | 12:22 - 13:50/ 9:30 - 10:30 - 11:50.
* OrderItem |  |  | 45
* Picture |  |  | 45
* Product |  |  | 45 |  | 11:55
* Product_Property |  |  | 45
* Property |  |  | 45
* Type |  |  | 45
* User |  |  | 45 |  | 13:30- 14:00 / 11:50
# Services og interfaces for: | All Complete in single day. |  | Etime | ActTime
* Order |  |  | 60 | 30
* OrderItem |  |  | 60 | 30
* Picture |  |  | 60 | 30
* Product |  |  | 60 | 30
* Product_Property |  |  | 60 | 30
* Property |  |  | 60 | 30
* Type |  |  | 60 | 30
* User |  |  | 60 | 30
* LogIn |  |  | 60 | 30
|  |  | 540 | 270 | rough estimate
# Tests for Services: |  |  | Etime | ActTime
*LogIn |  |  | 60
* Order |  |  | 60
* OrderItem |  |  | 60
* Picture |  |  | 60
* Product |  |  | 60
* Product_Property |  |  | 60
* Property |  |  | 60
* Type |  |  | 60
* User |  |  | 60
# Controllers for: |  |  | Etime | Acttime
* Order |  |  | 90
* OrderItem |  |  | 90
* Picture |  |  | 90
* Product |  |  | 90
* Product_Property |  |  | 90
* Property |  |  | 90
* Type |  |  | 90
* User |  |  | 90
*LogIn |  |  | 90
|  | Total: | 810
# Controllers Tests for: |  |  | Etime | Acttime
* Order |  |  | 60
* OrderItem |  |  | 60
* Picture |  |  | 60
* Product |  |  | 60
* Product_Property |  |  | 60
* Property |  |  | 60
* Type |  |  | 60
* User |  |  | 60
*LogIn |  |  | 60
# Misc:
* DB Migration, og Database opsættning. Time:20 min /10:36 - 10:42 /
# Angular Client:
*